## WDTH vs WDM
Turn on ALT vision inspection
KV machine time tracking and action plan
|  |  |  | CT Improvement ONLY |  | Software version |  |  | WDTH | [34 empty] | WDTH | [5 empty] | WDM | [31 empty] | WDM
[8 empty] | ConFig | [24 empty] | 10X | 10X | 10X | 10X | 10X | 10X | 10X | 6X | 10X | 10X | 10X | 10X | 10X | 10X | 10X | 6X | 10X | [25 empty] | 10X | 10X | 10X | 10X | 10X | 10X | 10X | 10X | 10X | 10X | 10X | 6X | 6X
Station | #tool | ZONE | Work | Site PIC | Leader | WDTH | WDM | CT TARGET | ww13 | ww14 | ww15 | ww16 | ww17 | ww20 | ww21 | ww22 | ww23 | ww24 | ww25 | ww26 | ww27 | ww28 | ww29 | ww30 | ww31 | ww32 | ww33 | ww34 | ww35 | ww36 | ww37 | ww38 | ww39 | ww40 | ww41 | WW42 | WW43 | WW44 | WW45 | WW46 | WW47 | WW48 | WW49 | WW50 | WW51 | WW52 | WW01 | WW02 | WW03 | WW19 | WW20 | WW21 | WW21 | WW22 | WW23 | WW24 | WW25 | WW26 | WW27 | WW28 | ww29 | ww30 | ww31 | ww32 | ww33 | ww34 | ww35 | ww36 | ww37 | ww38 | ww39 | ww40 | ww41 | ww42 | ww43 | ww44 | ww45 | ww46 | ww47 | ww48 | ww49 | ww50 | ww51 | ww52 | WW01 | WW02 | WW03 | Action plan | Expect gain | ECD Update | PIC | Remark
APFA Load | 1 | Zone1 | Buffer | Sara Prateep | Sara | AG.0S.01 | AG.0U.5 | 6.5
|  | Zone2 | Load APFA&Clamp pivot |  |  |  |  | 6.5 | ww13: N/A; ww14: N/A; ww15: 15.22; ww16: 19.25; ww17: 16; ww20: 12.63; ww21: 14.01; ww22: 11.81; ww23: 11.16; ww24: 10.43; ww25: 10.72; ww26: 10.92; ww28: 13.37; ww29: 11.55; ww30: 11.66; ww31: 10.65; ww32: 11; ww33: 10.51; ww34: 10.67; ww35: 10.53; ww36: 11.22; ww37: 9.88; ww38: 8.87 | 14.84 | 14.84 |  | 12.1 | 12.85 | 11.56 |  | 11.69 | 11.2 |  | 10 | 10.19 | 9.22 | 9.72 | 9.1 | 8.81 | 8.47 | 8.82 | 9.47 | 8.92 | 9.41 | 9.07 |  | 9.15 | [14 empty] | Review the working element to check operation time by step. | Wait time study from IE | 4 Dec - Done | Somboon Kanyarat | Need another 4s improvement to the total opportunities identified
[88 empty] | Current, operator need to insert and lock slider key to help on ACF LAM, found bubble issue from leveling. Need to put additional plate between lifter and clamp - check with Trimech team. - Done swap ACF LAM machine between 3rd and 4th line. | Wait time study from IE | 6 Nov - Done | Saravut Trimech
[88 empty] | Current, operator need to lock pivot clamp. Need to add pomalux pushing mechanism before lock pivot clamp (At zone 3). To update design date Design reeview will be done on Dec 2 | 1.5sec | 4 Dec - Done | Saravut Chaiya
[88 empty] | Eliminate pivot orientation - Proposal is done, get positive result. Plan to discuss in interlock meeting 17 Nov. Done discussion and get agreement. Will raise EB and training by 19 Nov. | 1.5sec | 19 Nov - Done | Somboon | Done - 1.6 sec gain
[88 empty] | Flex bracket holder redesign. To update design date Design review will be done on Dec 2 | 1sec | 4 Dec - Done | Chaiya
[88 empty] | New machine prototye will be available on end of February. Postpone to end of March. |  | E-March - Done | Chaiya | Done receive and setup in line.
|  | Zone3 | Clamp pivot (not able to work) |  |  |  |  | 6.5 | ww13: N/A; ww14: N/A; ww15: 5.62; ww16: 5.75; ww17: 5.65; ww20: 6.23; ww21: 5.46; ww22: 5.63; ww23: 5.23; ww24: 5.15; ww25: 5.13; ww26: 5.12; ww28: 5.34; ww29: 5.29; ww30: 5.34; ww31: 5.25; ww32: 5.23; ww33: 5.25; ww34: 5.26; ww35: 5.43; ww36: 6.25; ww37: 5.27; ww38: 5.23 | 6.04 | 6.04 |  | 6.08 | 6.05 | 6.02 |  | 4.43 | 6.36 |  | 6.21 | 6.19 | 6.35 | 6.32 | 5.22 | 4.57 | 3.88 | 4.34 | 4.43 | 3.87 | 3.88 | 4.1 |  | 4.1
New AFA Load | 1 | Zone1 | Buffer |  |  | AG.0W.05 | AG.0U.06 | 6.5 | ww38: N/A; 10X ww39: N/A; 10X WW03: 1.3 | [20 empty] | N/A | N/A
|  | Zone2 | Load AFA |  |  |  |  | 6.5 | ww38: N/A; 10X ww39: N/A; 10X ww41: 9.05; 10X WW43: 9.79; 10X WW44: 8.08; 10X WW45: 8.76; 6X WW46: 8.02; 10X WW47: 7.82; 10X WW48: 8.67; 10X WW49: 8.26; 10X WW50: 7.07; 10X WW51: 9; 10X WW52: 8.4; 10X WW01: 7.94; 6X WW02: 6.44; 10X WW03: 6.65 | [20 empty] | N/A | N/A |  | 9.25 | 8.26 | 7.22 | 7.15 |  | 7.3 | 6.11 | 7.34 | 6.48 | 6.69 | 6.65 | 6.2 | 7.35 | 6 |  | to check with production do we need to increase scanner WD
|  | Zone3 | Clamp Pivot and Flip |  |  |  |  | 6.5 | ww38: N/A; 10X ww39: N/A; 10X ww41: 10.54; 10X WW43: 8.01; 10X WW44: 5.97; 10X WW45: 6.2; 6X WW46: 5.92; 10X WW47: 5.5; 10X WW48: 5.58; 10X WW49: 5.52; 10X WW50: 5.53; 10X WW51: 5.45; 10X WW52: 5.52; 10X WW01: 5.76; 6X WW02: 4.14; 10X WW03: 4.17 | [20 empty] | N/A | N/A |  | 7.61 | 7.91 | 6.95 | 6.76 |  | 6.21 | 6.04 | 5.95 | 6.01 | 5.88 | 5.89 | 5.88 | 6.47 | 6.12 |  | k.Vichian to order upgrade parts for WDTH and prakash for WDM
ACF Laminate | 1 | Zone1 | Scan | Kannan Wanchai Thanakorn | Thanakorn | AY.00.04 | AY.00.13 | 6.5 | 1.96 | 1.71 | 1.65 | 1.68 | 1.68 | 1.94 | 1.91 | 1.9 | 1.89 | 1.91 | 1.9 | 1.91 |  | 1.95 | 1.94 | 1.91 | 1.96 | 1.95 | 2.28 | 1.89 | 1.92 | 1.94 | 2 | 1.91 |  |  | 2.1 |  | 2.13 | 2.14 | 2.14 | 2.17 | 2.15 | 2.23 | 2.22 | 2.16 | 2.03 | 1.84 | 1.85 | 1.86 | 1.87 | 1.92 | 1.92 | 1.92 | 2.02 | 2.02 | 2.77 |  | 2.28 | 2.23 |  | 2.19 | 2.22 | 2.21 | 2.21 | 2.11 | 2.11 | 2.15 | 2.36 | 2.26 | 2.4 | 2.39 | 2.4 |  | 2.4 | 2.37 | 2.23 | 2.21 |  | 2.24 | 2.32 | 2.2548 | 2.32 | 1.86 | 1.88 | 2.61 | 2.63 | 2.61
|  | Zone2 | Laminate |  |  |  |  | 6.5 | 6.98 | 6.79 | 6.79 | 6.96 | 7.02 | 8.64 | 8.7 | 8.66 | 8.67 | 8.75 | 8.7 | 6.88 |  | 8.4 | 6.89 | 6.61 | 6.98 | 7 | 6.97 | 6.82 | 7.26 | 7.37 | 6.87 | 5.88 |  |  | 6.3 |  | 5.36 | 6.36 | 6.33 | 7.17 | 6.3 | 6.32 | 7.83 | 7.86 | 7.43 | 7.42 | 7.41 | 7.46 | 6.72 | 9.45 | 9.32 | 9.5 | 7.69 | 7.14 | 6.93 |  | 7.59 | 7.62 |  | 7.64 | 6.93 | 6.84 | 6.54 | 6.56 | 6.6 | 6.68 | 6.35 | 6.4 | 6.42 | 6.41 | 6.41 |  | 6.2 | 6.21 | 6.21 | 6.21 |  | 6.56 | 7.01 | 6.4635 | 6.55 | 6.57 | 6.61 | 6.73 | 6.51 | 7.27 |  | Cooperate with Trimech to fix the high CT. Kannan will share the goodness from WDM to WDTH site. |  | 2 Dec - Done
|  | Zone3 | Inspection |  |  |  |  | 6.5 | 9.28 | 12.42 | 5.12 | 11.92 | 8.39 | 9.62 | 7.68 | 6.1 | 5.9 | 6.52 | 6.39 | 6.78 |  | 6.59 | 5.68 | 6.45 | 4.91 | 5.13 | 5.38 | 5.49 | 6.2 | 5.51 | 5.25 | 4.59 |  |  | 6.38 |  | 6.31 | 4.82 | 5.56 | 4.55 | 5.42 | 6 | 5.75 | 4.85 | 6.78 | 4.97 | 6.47 | 4.89 | 5.5 | 6.98 | 9.03 | 9.61 | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Already receive new camera. Under setup, fine tune and rerun correlation |  | ww44 | Narasimha Thanakorn
[88 empty] | Remove ACF film VMI validation and software check and move the function to 1st station in the HGA loading. | 1.0 sec | WDM - 20 Nov - Done WDTH - 21 Nov - Done | Gan/Somboon
[88 empty] | Checking current setting in 2303AB line compare to WDM line. |  | 12 Dec - Done | Wanchai Kannan
[88 empty] | Optimize new parameter, reduce holding time from 2 sec to 1.5 sec + increase temp (ww32) - Kannan | 0.5 sec | ww32 - Done | Saravut | Actual 0.4 sec gain.
[88 empty] | Remove off-set value from X-Y stop position to match with bond head. | 1.0 sec | 12 Dec - Done | Saravut
Autostacker
SFlip + Swage | 1 | Zone1 | Scan & (Only Flipper) | Naim Sakda | Sakda | AP.0A.0A | AP.09.66 | 6.5 | 10X WW03: 1.3 | 3.9 | 3.81 | 3.77 | 3.32 | 3.67 | 3.89 | [32 empty] | Evaluate to use 2 swage balls process. Both 80.0-81.0 and 80.5-81.0 recipe show the positive result. Cross section show comparable boss engagement quality between POR and evaluation group. Will check on swage torque from POR swage ball without pre-swage IPA as backup data. | 3.0 sec | 12 Dec - Done | Somboon Prakash | K. Somboon to send the complete package by Monday (22nd Dec)
|  | Zone2 | Flip (Only Sflip + Swage) |  |  |  |  | 6.5 | 3.86 | 4.1 | 3.64 | 4.21 | 4.19 | N/A | 4.17 | 3.59 | 3 | 3.19 | 3.05 | 3.27 |  | 2.91 | 2.95 | 2.91 | 2.92 | 2.94 | 2.97 | 2.9 | 3.56 | 2.94 | 2.93 | 2.95 |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1.94 |  |  |  |  | N/A | N/A |  | 2.86 | 2.85 |  | 2.85 | 2.85 | 2.88 | Skip | Skip | Skip | Skip | Skip | Skip | Skip | 2.05 | 2.06 |  | 2.06 | 2.06 | 2.06 | 2.06 |  | 1.93 | 1.98 | 1.91 | 2.04 | 1.94 | 1.9 | 1.91 | 1.9 | 1.94 |  | Discuss with DE on 2 balls swaging process for implementation plan. | 5.0 sec | ww46 | Somboon | Done CRB review, awaiting drive 1K build evaluation.
|  | Zone3 | Swage |  |  |  |  | 17 | [6 empty] | 23.29 | 23.79 | 24.04 | 24.13 | 23.81 | 20.68 |  | 23.1 | 23.16 | 23.23 | 23.22 | 23.21 | 23.12 | 23.09 | 23.12 | 23.68 | 23.77 | 21.27 |  |  | 24.87 |  | 22.87 | 22.97 | 22.92 | 22.31 | 21.76 | 22.04 | 21.47 | 23.5 | 25.73 | 21.23 | 23.62 | 22.09 | 22.47 |  |  |  |  | N/A | N/A |  | 22.14 | 22.11 |  | 22.15 | 22.61 | 22.57 | Skip | Skip | Skip | Skip | Skip | Skip | Skip | 22.91 | 22.81 |  | 22.75 | 22.65 | 21.98 | 22.02 |  | 25.56 | 23.82 | 24.07 | 22.84 | 22.87 | 22.47 | 22.31 | 22.12 | 22.91 |  | Increase nozzle down speed and brake before reach target. Need to modify swage plate by add shock absorber. Need to check on hardware modification. Prakash will share ECD from vendor on 3 Dec. | 2.0 sec | 3 Dec - Done | Saravut | Design completed. Prototype in process. Vendor will send the parts on Monday (22nd Dec)
Swage | 3 | Zone1 | Swage | Naim Sakda | Sakda | AP.0A.0A | AP.0A.03 | 17 | 21.85 | 21.82 | 21.83 | 21.63 | 22.33 | 23.24 | 22.69 | 23.15 | 23.17 | 23.96 | 23.95 | 23.98 |  | Skip | 25.95 | 20.38 | Skip | Skip | 20.8 | 21.92 | 23.66 | 22.54 | 22.97 | 21.78 |  |  | 21.02 |  | 21.63 | 21.65 | 20.72 | 20.42 | 20.55 | 20.86 | 21.16 | 21.81 | 20.76 | 20.44 | 20.35 | 20.24 | 21.03 | 22.82 | 24.4 | 24.28 | 23.89 | 23.56 | 23.1 |  | 21.93 | 22.01 |  | 21.99 | 21.96 | 20.27 | 20.35 | 21.55 | 21.65 | 22.37 | 22.24 | 22.33 | 22.27 | 22.97 | 22.06 |  | 22.15 | 21.98 | 21.3 | 21.56 |  | 22.34 | 22.01 | 22.2074 | 22.19 | 22.35 | 22.18 | 22.21 | 22.51 | 22.2 |  | Shorter stroke for nozzle and faster nozzle retract | 0.35 sec | 2014-11-07 | Saravut | Current tool already in max speed
|  | Zone2 | Buffer |  |  |  |  | 17 | [79 empty] | By pass new version released .08(WDTH) |  | ww42 | Surapong | Preliminary testing was done and get good result. Under monitoring.
|  | Zone3 | Swage |  |  |  |  | 17 | 22.01 | 23.21 | 22.88 | 21.98 | 21.45 | 21.93 | 21.86 | 21.92 | 22.11 | 22.14 | 21.93 | 22.11 |  | 21.82 | 21.46 | 20.31 | 20.26 | 20.69 | 20.64 | 21.05 | 24.78 | 23.38 | 23.17 | 22.28 |  |  | 21.43 |  | 23.44 | 24.31 | 22.2 | 22.01 | 22.01 | 23.06 | 22.28 | 23.48 | 22.79 | 23.86 | 23.65 | 21.83 | 22.88 | 23.56 | 24.6 | 24.74 | 23.64 | 23.21 | 22.52 |  | 22.79 | 22.86 |  | 22.85 | 22.76 | 22.84 | 21.65 | 22.08 | 22.12 | 21.55 | 21.65 | 21.78 | 21.68 | 22.56 | 21.86 |  | 21.95 | 21.53 | 22.85 | 22.84 |  | 24.05 | 25.03 | 24.08 | 23.76 | 23.8 | 22.87 | 22.54 | 22.32 | 22.38
ALT | 2 | Zone1 | Vision | Kannan Wanchai | Kannan | B7.03.01 | EV_02.17 | 12 | 3.75 | 3.8 | 3.89 | 3.87 | 3.87 | 3.89 | 3.77 | 4.6 | 4.59 | 4.06 | 4.32 | 5.46 |  | 4.89 | 4.14 | 4.49 | 4.32 | 4.46 | 4.52 | 4.14 | 4.15 | 4.18 | 4.21 | 4.2 |  |  | 4.06 |  | 4.15 | 4.17 | 3.88 | 3.86 | 3.88 | 3.85 | 3.87 | 3.89 | 3.89 | 3.86 | 3.96 | 3.92 | 3.87 | 3.54 | 3.61 | 3.53 | 3.47 | 3.39 | 3.4 |  | 3.39 | 3.39 |  | 3.43 | 3.43 | 3.41 | 3.7 | 3.63 | 3.63 | 3.63 | 3.63 | 3.63 | 3.61 | 3.6 | 3.7 |  | 3.7 | 3.71 | 3.85 | 3.82 |  | 3.73 | 3.61 | 3.82 | 3.88 | 3.75 | 3.7556 | 3.6 | 3.61 | 3.88
|  | Zone2 | Align&Mark |  |  |  |  | 12 | 14.11 | 13.46 | 12.68 | 13.91 | 15.34 | 15.75 | 14.24 | 14.76 | Skip | 14.25 | 15.21 | Skip |  | 14.9 | 13 | 18.85 | 12.7 | 14.04 | 13.89 | 11.76 | 11.93 | 12.62 | 12.55 | 12.2 |  |  | 13.09 |  | 12.79 | 12.35 | 10.91 | 10.74 | 11.1 | 11.04 | 11.49 | 11.42 | 11.27 | 11.16 | 11.35 | 11.49 | 11.53 | 12.57 | 12.87 | 12.82 | 11.76 | 11.36 | 11.64 |  | 11.76 | 12.48 |  | 12.93 | 12.95 | 11.8 | 11.81 | 11.66 | 11.36 | 11.89 | 11.35 | 12.06 | 11.86 | 11.98 | 12.47 |  | 11.89 | 11.92 | 11.15 | 12 |  | 16.94 | 13.29 | 12.8 | 13.85 | 11.84 | 12.6116 | 12.36 | 12.11 | 11.12 |  | Optimize X axis. Share the data to WDTh Find opertunity for another 0.2 sec | 0.8sec | 14 Nov - Done | Kannan Wanchai | Need 1.0 sec total improvement
[88 empty] | Replicate parameter setting from Zone 3 to Zone 2 Kannan to send parameter details to WDTH |  | 28 Nov - Done | Kannan | WDTh to cut in ver 16. train operators on TSA misalignment
|  | Zone3 | Align&Mark |  |  |  |  | 12 |  | 13.35 | 12.39 | 12.88 | 13.35 | 14.74 | 12.83 | 13.15 | 14.52 | 14.83 | 15.33 | 14.32 |  | 14.39 | 12.49 | 14.84 | 13.08 | 13.91 | 13.95 | 13.77 | 11.56 | 12.84 | 12 | 12.16 |  |  | 11.22 |  | 12.34 | 12.18 | 10.85 | 10.47 | 10.78 | 10.78 | 11.18 | 11.18 | 11.07 | 10.96 | 12.19 | 11.14 | 11.35 | 12.66 | 12.05 | 11.91 | 12.77 | 12.01 | 11.5 |  | 11.25 | 13.44 |  | 12.29 | 12.23 | 11.53 | 11.6 | 11.43 | 11.98 | 11.98 | 11.83 | 12.32 | 12 | 12.13 | 12.96 |  | 11.56 | 11.89 | 11.53 | 11.96 |  | 14.47 | 14.61 | 13.82 | 14.3 | 12.41 | 13.35 | 11.56 | 11.51 | 11.23 |  | Observe first yield in WDTH is too low. May consider to use AWS navigator. |  | 12 Dec - Done | Wanchai | WDTh need to cut in by this week
ACF Finalbond | 2 | Zone1 | Vision | Kannan Wanchai | Kannan | GA.AZ.04 | AZ.00.17 | 12 | 1.98 | 1.98 | 1.96 | 1.98 | 1.98 | 1.97 | 1.99 | 1.99 | 1.98 | 1.99 | 1.99 | 1.99 |  | 1.99 | 1.99 | 2.01 | 1.98 | 2.01 | 1.91 | 1.9 | 1.89 | 1.89 | 1.9 | 1.9 |  |  | 1.89 |  | 1.89 | 1.93 | 1.93 | 1.98 | 2.09 | 2.11 | 2.21 | 2.05 | 1.8 | 1.8 | 1.82 | 1.46 | 1.47 | 2.22 |  | 1.89 | 1.9 | 2.02 | 1.89 |  | 1.89 | 1.89 |  | 1.87 | 1.99 | 1.89 | 1.93 | 2.11 | 1.93 | 1.93 | 2.16 | 1.86 | 1.91 | 1.94 | 1.92 |  | 1.93 | 1.93 | 1.88 | 1.99 |  | 2.04 | 2.57 | 3.0009 | 3.05 | 3.0777 | 3.2858 | 2.65 | 3.265 | 3.3599 |  | To WDM tester to sub 12s similar to WDTH | 2.8s | 14 Nov - Done | Kannan | WDM to bridge gap
|  | Zone2 | Final bond |  |  |  |  | 12 | 12 | 14.6 | 11.38 | 11.54 | Skip | 13.03 | 13.17 | 13.08 | 13.13 | 11.56 | 12.64 | 11.7 |  | 11.64 | 11.72 | n/a | Skip |  | 13.29 | 11.86 | Skip | 12.17 | 12.04 | 12.07 |  |  | 12.06 |  | 12.14 | 12.3 | 13.13 | 12.82 | 12.67 | 12.7 | 13.06 | 13.11 | 13.31 | 12.64 | 12.97 | 11.26 | 11.25 | 14.68 | 14.76 | 12.46 | 11.99 | 11.93 | 11.93 |  | 13.97 | 12.09 |  | 11.56 | 12.68 | 11.83 | 12.39 | 12.29 | 12.31 | 12.83 | 12.09 | 11.96 | 12 | 11.8 | 11.91 |  | 11.91 | 11.92 | 12.51 | 12.5 |  | 14.13 | 13.01 | 12.95 | 12.65 | 11.78 | 11.72 | 12.2 | 12.3701 | 12.1511 |  | Standardize the holding time to 7Sec Need to check X-Y position on lifter. |  | 2 Dec - Done | Saravut | Check the WDM CT
|  | Zone3 | Final bond |  |  |  |  | 12 | 11.52 | 11.59 | Skip | Skip | 11.44 | 11.8 | Skip | Skip | Skip | Skip | 12.41 | 11.61 |  | 11.73 | 11.72 | 12.13 | 12.07 | 12.21 | 13.25 | 11.65 | 12.06 | 12 | 11.8 | 11.81 |  |  | 11.84 |  | 11.85 | 12.41 | 12.57 | 12.44 | 12.56 | 12.61 | 13.06 | 12.36 | 11.92 | 12.04 | 12.12 | 11.19 | 11.18 | 14.64 | 14.48 | 12.45 | 11.97 | 11.93 | 11.89 |  | 13.12 | Skip |  | Skip | Skip | 11.87 | 12.18 | 11.98 | 12.16 | 13.57 | 12.16 | 12.09 | 11.94 | 11.91 | 11.71 |  | 11.86 | 11.93 | 12.61 | 12.87 |  | 13.6 | 11.68 | 12.5377 | 11.66 | 11.63 | 11.6697 | 11.53 | 12.3304 | 12.0762 |  | Follow up with simha to improve idle temp profile |  | 28 Nov - Done | Somboon | Kannan to travel to WDTh and share the parameter to WDTH again by Today (16th Dec)
Jet | 2 | Zone1 | Vision | Naim Prateep Arnon | Arnon | B5.02.23 | B5.01.03 | 12 | 3.72 | 3.79 | Skip | 3.74 | 3.76 | 3.81 | 3.95 | 3.81 | 4.91 | 4.27 | 4.26 | 4.31 |  | 4.3 | 4.6 | 4.46 | 4.25 | 5.4 | 4.63 | 3.99 | 6.44 | 5.4 | 5.45 | 5.83 |  |  | 3.72 |  | 4.39 | 4.32 | 4.18 | 4.1 | 4.34 | 4.27 | 4.47 | 7.46 | 6.56 | 4.17 | 4.3 | 4.17 | 4.33 | 4.83 | 4.96 | 4.8 | 4.89 | 4.7 | 3.35 |  | 3.44 | 3.58 |  | 4.03 | 3.69 | 3.7 | 3.89 | 3.75 | 3.56 | 3.56 | 3.75 | 3.77 | 3.77 | 3.8 | 3.73 |  | 3.73 | 3.73 | 3.8 | 3.85 |  | 3.91 | 3.97 | 4.1413 | 4.16 | 4.06 | 4.05 | 4.24 | 4.08 | 3.968
|  | Zone2 | Tack |  |  |  |  | 12 | 15.12 | 16.11 |  | 15.27 | 16.67 | 17.61 | Skip | Skip | 16.88 | 14.44 | 11.5 | 12.1 |  | 12.16 | 13.69 | 11.88 | 14.04 | 12.86 | 12.02 | 11.97 | 14.19 | 11.9 | 14.09 | 13.89 |  |  | 13.1 |  | 11.86 | 12.06 | 11.94 | 8.94 | 11.8 | 11.48 | 12.95 | 14.35 | 13.99 | 12.95 | 12.96 | 9.98 | 13.09 |  |  |  | Skip | Skip | Skip |  | 11.67 | 11.91 |  | 11.97 | 11.67 | 11.85 | 11.9 | 11.62 | 11.67 | 11.52 | 8.71 | 8.68 | 8.86 | 11.8 | 8.9 |  | 11.87 | 11.85 | 11.87 | 11.88 |  | 11.89 | 11.82 | 11.87 | 11.99 | 11.85 | 11.91 | 11.91 | 11.17 | 8.5897 |  | With latest recipe, JET dispensing perfome better dot size and position. Plan to validate and optimize / increase robot speed. To get an overall plan for 12 sec. | 4.0 sec | 18 Nov - Done | Naim Arnon | Share new code to WDM for evaluation by today(19th Dec)
|  | Zone3 | Tack |  |  |  |  | 12 | Skip | Skip |  | Skip | Skip | Skip | 17.45 | 17.4 | 17.4 | 15.21 | 11.5 | Skip |  | Skip | 12.5 | 12.43 | 12.1 | 12.37 | 11.78 | Skip | 13.3 | Skip | 12.8 | 13.63 |  |  | 12.62 |  | 11.65 | 11.73 | 11.86 | 8.87 | 10.44 | 11.29 | 13.05 | 14.21 | 13.8 | 12.74 | 12.86 | 9.81 | 12.76 | 22.62 | 21.99 | 16.39 | 15.88 | 14.25 | 11.73 |  | 11.85 | 11.87 |  | 11.9 | 11.94 | 11.95 | 11.98 | 11.56 | 11.65 | 11.61 | 8.62 | 8.59 | 8.56 | 11.92 | 8.64 |  | 11.95 | 11.96 | 11.95 | 11.92 |  | 11.99 | 11.86 | 11.91 | 11.95 | 11.92 | 11.93 | 11.89 | 11.32 | 8.7001 |  | WDM - Change to use nozzle 0.4 mm. with 6 rows tacking same as WDTH (Already use 0.4mm nozzle insert) |  | 25 Nov - Done | Nitipat | Evaluate new code for CT improvement
UV | 2 | Zone1 | Cure | Naim Sakda | Prakash | AC.0R.01/ GA.AC.0R | AC.0P.01 | 6.5 | 30.65 | 30.47 | 30.67 | 30.74 | 31.25 | 30.46 | 30.46 | 30.46 | 7.96 | 7.96 | 7.96 | 7.97 |  | 7.96 | 6.97 | 6.96 | 6.97 | 6.97 | 6.97 | 6.97 | 6.97 | 6.97 | 6.97 | 6.97 |  |  | 6.97 |  | 6.46 | 6.46 | 6.46 | 6.46 | 6.49 | 6.46 | 6.46 | 6.46 | 6.46 | 6.46 | 6.46 | 6.46 | 6.46 | 30.45 | 30.45 | 30.45 | 30.45 | 30.45 | 30.45 |  | 7.94 | 7.94 |  | 7.94 | 6.94 | 6.94 | 6.94 | 6.94 | 7.14 | 6.94 | 6.94 | 6.94 | 6.94 | 6.94 | 6.94 |  | 6.94 | 6.44 | 6.44 | 6.44 |  | 6.44 | 6.44 | 6.44 | 6.44 | 6.44 | 6.44 | 6.44 | 6.44 | 6.44 |  |  | To meet 6.5 sec CT | 4 Dec - Done | Somboon | Need discuss on using new out gassing spec of 55K. Discuss with John Hanke
|  | Zone2 | Cure |  |  |  |  | 6.5 | 30.44 | 30.49 | 30.38 | 30.97 | 30.29 | 30.44 | 30.44 | 30.44 | 7.94 | 7.94 | 7.94 | 7.94 |  | 7.95 | 6.94 | 6.94 | 6.95 | 6.95 | 6.95 | 6.95 | 6.95 | 6.95 | 6.94 | 6.95 |  |  | 6.95 |  | 6.45 | 6.44 | 6.46 | 6.47 | 6.48 | 6.46 | 6.46 | 6.46 | 6.46 | 6.46 | 6.46 | 6.46 | 6.46 | 30.45 | 30.45 | 30.45 | 30.45 | 30.45 | 30.45 |  | 7.95 | 7.95 |  | 7.95 | 6.95 | 6.95 | 6.95 | 6.95 | 7.14 | 6.95 | 6.95 | 6.95 | 6.95 | 6.95 | 6.95 |  | 6.95 | 6.44 | 6.44 | 6.44 |  | 6.44 | 6.44 | 6.44 | 6.44 | 6.44 | 6.44 | 6.44 | 6.44 | 6.44 |  | New code to split the UV curing to 4 zones. Validate new code in WDM 2nd line |  | 18 Nov - Done | Nitipat
|  | Zone3 | Buffer |  |  |  |  | 6.5 | [79 empty] | Find the way to increase the light intensity. May consider to use prism, lens or mirror. |  | 2014-11-14 | Saravut
UV Mirror | 2 | Zone1 | Cure | Naim Sakda |  |  |  | 6.5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 30.59 | 7.97 | 7.97 | 7.99 | 8.04 |  | 7.99 | 6.98 | 7.06 | 7.08 | 7.08 | 7.09 | 7.08 | 7.08 | 6.99 | 6.97 | 6.97 |  |  | 6.98 |  | 6.47 | 6.47 | 6.49 | 6.47 | 6.48 | 6.46 | 6.47 | 6.47 | 6.46 | 6.47 | 6.47 | 6.47 | 6.46 | N/A | N/A | N/A | N/A | N/A | N/A |  | 7.95 | 7.95 |  | 7.95 | 6.95 | 6.95 | 6.95 | 6.95 | 6.95 | 6.95 | 6.95 | 6.95 | 6.95 | 6.95 | 6.95 |  | 6.95 | 6.45 | 6.45 | 6.45 |  | 6.45 | 6.45 | 6.45 | 6.45 | 6.45 | 6.45 | 6.45 | 6.45 | 6.45 |  | Optimize the UV chamber to get the higher light intensity. - Draft is done. |  | 11 Nov - Done | Prachearn
|  | Zone2 | Cure |  |  |  |  | 6.5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 30.76 | 7.97 | 7.96 | 8 | 8.03 |  | 7.99 | 6.97 | 7.07 | 7.08 | 7.07 | 7.09 | 7.08 | 7.08 | 6.98 | 6.97 | 6.98 |  |  | 9.8 |  | 6.46 | 6.46 | 6.47 | 6.48 | 6.47 | 6.46 | 6.47 | 6.47 | 6.46 | 6.47 | 6.47 | 6.47 | 6.46 | N/A | N/A | N/A | N/A | N/A | N/A |  | 7.94 | 7.94 |  | 7.94 | 6.94 | 6.94 | 6.94 | 6.94 | 6.95 | 6.95 | 6.95 | 6.95 | 6.95 | 6.95 | 6.95 |  | 6.95 | 6.45 | 6.45 | 6.45 |  | 6.445 | 6.445 | 6.445 | 6.445 | 6.45 | 6.45 | 6.45 | 6.45 | 6.45 |  | Evaluate shorter curing time 5.0, 5.5 and 6.0 sec 4 times curing. | 1.5 sec | ww41 - Done | Somboon | Preliminary result is pass. Re-evaluate with Silane free epoxy. Result show pass all group, document is updated and full approved.
|  | Zone3 | Buffer |  |  |  |  | 6.5 | [79 empty] | Split code cut in with Mitec on |  | Done | Haris/Darren
BTI | 1 | Zone1 | Scan | Gan Koy | Koy | GA.AE.0M | AE.0H.07 | 6.5 | [79 empty] | Reduce inspection time 1 sec/frame (reduce 0.5 sec/point) |  |  |  | Need a timeline nd 1.8s opportunity Need newcode to enable bond pad and flexture validation only.
|  | Zone2 | Inspection |  |  |  |  | 6.5 | N/A | N/A | N/A | N/A | N/A | 8.23 | 8.23 | 8.21 | 8.21 | 8.21 | 8.18 | 8.18 |  | 7.67 | 7.7 | 8.04 | Skip | 7.32 | 7.34 | 8.39 | 6.31 | 6.3 | 6.32 | 6.35 |  |  | 8.38 |  | 6.19 | 6.19 | 6.35 | 6.3 | 6.34 | 6.36 | 6.33 | 6.33 | 6.33 | 6.33 | 8.38 | 6.26 | 6.35 | N/A | N/A | N/A | N/A | N/A | N/A |  | 5.58 | 10.1 |  | 10.1 | 10.1 | 10.1 | 10.1 | 10.1 | 10.1 | 10.1 | 5.6 | 5.6 | 5.6 | 5.6 | 5.6 |  | 5.6 | 5.6 | 5.6 | 5.6 |  | 5.6 | 5.6 | 5.6 | 5.6 | 5.6 | 5.6 | 5.6 | 5.6 | 5.6 |  | Consider to change to photo taking by 1 direction. | 1.0 sec | ww28 - Done | Saravut
|  | Zone3 | Buffer |  |  |  |  | 6.5
CT 1 | 2 | Zone1 | CT Test | Sara Somboon | Somboon | B2.04.05 | B2.04.04 | 12 | ww13: 8.81; ww14: 9.82; ww15: 10.06; ww16: 9.9; ww17: 9.42; ww20: 9.29; ww21: 9.05; ww22: 9.42; ww23: 9.09; ww24: 10.08; ww25: 9.22; ww26: 8.82; ww28: 9.05; ww29: 10.6; ww30: 10.53; ww31: 12.17; ww32: 11.38; ww33: 14.9; ww34: 12.65; ww35: 11.87; ww36: 10.11; ww37: 10.65; ww38: 9.99 | 10.72 | 10.86 | N/A | 10.34 | 9.24 | 9.69 |  | 9.45 | 9.68 |  | 9.56 | Skip | 9.95 | 10.03 | 8.61 | 8.77 | 9.24 | 9.21 | 9 | 8.05 | 9.1 | 8.25 |  | 9.62 | [14 empty] | To relayout Unload station. CT after ACF, Unload 1 and Unload 2 (with Auto shipping comb insert) - simulation | 6.0 sec | ww19 - Done | Anongnart Andrew
|  | Zone2 | Flip & Remove alignment pin & Unlock key |  |  |  |  | 12 | ww13: 10.19; ww14: 9.68; ww15: 10.1; ww16: 8.64; ww17: 8.03; ww20: 7.81; ww21: 8.76; ww22: 8.57; ww23: 8.7; ww24: 8.71; ww25: 9.49; ww26: 10.39; ww28: 8.45; ww29: 8.53; ww30: 8.67; ww31: 8.72; ww32: 9.39; ww33: 9.79; ww34: 10.38; ww35: 8.38; ww36: 8.4; ww37: 8.44; ww38: 8.45 | 6.88 | 6.53 | N/A | 6.47 | 6.6 | 6.66 |  | 5.62 | 5.63 |  | 5.62 | Skip | 6.03 | 5.72 | 6.51 | 6.56 | 6.58 | 6.63 | 6.65 | 6.7 | 6.56 | 6.47 |  | 6.48 | [14 empty] | Design is done, will have design review on 3 Dec. |  | 3 Dec - Done | Chaiya
|  | Zone3 | Remove key & Comb install |  |  |  |  | 12 | ww13: 18.3; ww14: 13.61; ww15: 17.47; ww16: 14.82; ww17: 16.05; ww20: 13.13; ww21: 14.51; ww22: 13.84; ww23: 15.03; ww24: 14.47; ww25: 14.01; ww26: 15.5; ww28: 14.82; ww29: 13.44; ww30: 15.56; ww31: 14; ww32: 13.38; ww33: 13.31; ww34: 11.92; ww35: 11.11; ww36: 12.03; ww37: 11.71; ww38: 10.47 | 14.33 | 14.57 | N/A | 13.86 | 12.37 | 13.25 |  | 13.9 | 14.68 |  | 14.02 | Skip | 12.65 | 12.63 | 12.13 | 12.11 | 12.66 | 12.56 | 10.45 | 10.74 | 10.97 | 12.24 |  | 11.96 | [14 empty] | Design is done, will have design review on 3 Dec. |  | 3 Dec - Done | Chaiya
CT 2 | 2 | Zone1 | CT Test |  |  |  |  | 12 | ww13: N/A; ww14: N/A; ww15: N/A; ww16: N/A; ww17: N/A; ww20: N/A; ww21: 9.86; ww22: 9.95; ww23: 9.99; ww24: 10.19; ww25: Skip; ww26: 9.82; ww28: 9.81; ww29: 11.44; ww30: 10.57; ww31: 10.58; ww32: 10.45; ww33: 10.55; ww34: 10.86; ww35: 14.93; ww36: 14.11; ww37: 10.47; ww38: 10.48 | N/A | N/A | N/A | 10.29 | 9.3 | 9.52 |  | 9.37 | 9.81 |  | 9.74 | 8.28 | 9.93 | 9.95 | 8.72 | 8.85 | 9.22 | 9.17 | 9.12 | 8.86 | 10.22 | 8.68 |  | 9.52 | [14 empty] | Shuttle clamp modification to improve load/unload process. Preliminary result from prototype is positive. Plan to 100% implement by ww22. |  | ww24 | Prakash | Send samples to WDTh and waiting for eval report for 100% polpulation
|  | Zone2 | Flip & Remove alignment pin & Unlock key |  |  |  |  | 12 | ww13: N/A; ww14: N/A; ww15: N/A; ww16: N/A; ww17: N/A; ww20: N/A; ww21: 7.73; ww22: 7.77; ww23: 7.75; ww24: 7.77; ww25: Skip; ww26: 7.76; ww28: 7.75; ww29: 7.76; ww30: 7.75; ww31: 7.72; ww32: 7.7; ww33: 7.7; ww34: 7.68; ww35: 7.73; ww36: 7.79; ww37: 7.79; ww38: 7.77 | N/A | N/A | N/A | 6.06 | 6.15 | 6.03 |  | 5.36 | 5.41 |  | 5.37 | 5.3 | 5.36 | 5.53 | 6.61 | 6.62 | 6.69 | 6.8 | 6.67 | 6.68 | 6.77 | 6.82 |  | 6.78
|  | Zone3 | Remove key & Comb install |  |  |  |  | 12 | ww13: N/A; ww14: N/A; ww15: N/A; ww16: N/A; ww17: N/A; ww20: N/A; ww21: 14.99; ww22: 13.24; ww23: 14.42; ww24: 14.15; ww25: Skip; ww26: 13.86; ww28: 14.43; ww29: 13.59; ww30: 14.28; ww31: 14.4; ww32: 13.22; ww33: 12.62; ww34: 13.44; ww35: 12.82; ww36: 13.38; ww37: 12.48; ww38: 10.48 | N/A | N/A | N/A | 14.76 | 12.2 | 13.07 |  | 14.2 | 15.91 |  | 14.15 | 13.58 | 13.29 | 12.95 | 12.35 | 10.82 | 12.97 | 12.22 | 11.33 | 10.98 | 11.93 | 11.96 |  | 11.25 | [17 empty] | Somboon | Paint the landscape for 12sec
Dual e-CT | 2 | Zone1 | CT Test |  |  | BC.02.03 | WDTH : BC.01.01 | 12 | ww38: N/A; 10X ww39: N/A; 10X ww41: 10.21; 10X WW43: 10.22; 10X WW44: 10.37; 10X WW45: 10.41; 6X WW46: 8.64; 10X WW47: 10.17; 10X WW48: 10.29; 10X WW49: 10.26; 10X WW50: 10.26; 10X WW51: 10.31; 10X WW52: 10.31; 10X WW01: 10.03; 6X WW02: 8.99; 10X WW03: 10.54 | [20 empty] | N/A | N/A |  | 9.61 | 9.31 | 9.66 | 9.36 |  | 9.83 | 11.48 | 10.13 | 9.59 | 9.05 | 9.76 | 10.21 | 9.34 | 9.97
|  | Zone2 | CT Test |  |  |  |  | 12 | ww38: N/A; 10X ww39: N/A; 10X ww41: 11.51; 10X WW43: 10.95; 10X WW44: 10.72; 10X WW45: 10.8; 6X WW46: 8.87; 10X WW47: 10.57; 10X WW48: 10.82; 10X WW49: 10.55; 10X WW50: 10.57; 10X WW51: 10.51; 10X WW52: 10.7; 10X WW01: 10.69; 6X WW02: 9.27; 10X WW03: 10.39 | [20 empty] | N/A | N/A |  | 9.75 | 10.15 | 9.89 | 9.36 |  | 9.81 | 9.96 | 9.75 | 10.01 | 9.42 | 9.88 | 10.45 | 9.67 | 9.07
|  | Zone3 | Buffer |  |  |  |  | 6.5 | ww38: N/A; 10X ww39: N/A | [20 empty] | N/A | N/A
Flip Comb Install (FCI) | 2 | Zone1 | Remove Alignment Pin |  |  | BB.00.01 | WDTH : BB.00.01 | 6.5 | ww38: N/A; 10X ww39: N/A; 10X ww41: 5.4; 10X WW43: 5.51; 10X WW44: 5.74; 10X WW45: 5.11; 6X WW46: 5.05; 10X WW47: 5.03; 10X WW48: 4.77; 10X WW49: 4.67; 10X WW50: 4.69; 10X WW51: 4.69; 10X WW52: 4.69; 10X WW01: 4.78; 6X WW02: 4.76; 10X WW03: 4.48 | [20 empty] | N/A | N/A |  | 4.69 | 4.68 | 4.68 | 4.75 |  | 4.55 | 2.97 | 3.1923 | 3.06 | 3.0091 | 2.7324 | 2.82 | 3.1312 | 3.05 |  | pull alighment impact to
|  | Zone2 | Flip & Remove slide key |  |  |  |  | 6.5 | ww38: N/A; 10X ww39: N/A; 10X ww41: 5.65; 10X WW43: 5.86; 10X WW44: 6.24; 10X WW45: 5.71; 6X WW46: 5.77; 10X WW47: 5.74; 10X WW48: 5.72; 10X WW49: 5.68; 10X WW50: 5.96; 10X WW51: 5.8; 10X WW52: 5.69; 10X WW01: 5.74; 6X WW02: 5.83; 10X WW03: 5.4 | [20 empty] | N/A | N/A |  | 4.77 | 4.76 | 4.77 | 4.23 |  | 4.46 | 4.49 | 4.747 | 4.4 | 4.3755 | 4.2747 | 4.38 | 4.4438 | 4.53
|  | Zone3 | Install Comb |  |  |  |  | 6.5 | ww38: N/A; 10X ww39: N/A; 10X ww41: 7; 10X WW43: 6.77; 10X WW44: 6.24; 10X WW45: 5.92; 6X WW46: 5.48; 10X WW47: 6.08; 10X WW48: 5.15; 10X WW49: 7.64; 10X WW50: 7.33; 10X WW51: 6.03; 10X WW52: 7.67; 10X WW01: 8.5; 6X WW02: 7.15; 10X WW03: 7.1 | [20 empty] | N/A | N/A |  | 6.57 | 6.91 | 7.14 | 7.38 |  | 6.94 | 7.88 | 7.9186 | 7.49 | 7.0954 | 7.3467 | 6.82 | 7.3132 | 6.84
Unload | 2 | Zone1 | Unclamp Pivot |  |  | BA.03.2 | WDTH : .BA.03.1 | 6.5 | ww38: N/A; 10X ww39: N/A; 10X ww41: 4.19; 10X WW43: 4.65; 10X WW44: 4.49; 10X WW45: 3.85; 6X WW46: 3.76; 10X WW47: 3.72; 10X WW48: 3.72; 10X WW49: 3.78; 10X WW50: 3.8; 10X WW51: 3.69; 10X WW52: 3.76; 10X WW01: 3.73; 6X WW02: 3.68; 10X WW03: 3.72 | [20 empty] | N/A | N/A |  | 3.5 | 3.59 | 3.68 | 3.58 |  | 3.76 | 3.7 | 3.69 | 3.74 | 3.8 | 3.75 | 3.6 | 3.59 | 3.78
|  | Zone2 | Unlock flex from slot and unload |  |  |  |  | 6.5 | ww38: N/A; 10X ww39: N/A; 10X ww41: 10.46; 10X WW43: 8.34; 10X WW44: 8.48; 10X WW45: 8.99; 6X WW46: 7.19; 10X WW47: 7.21; 10X WW48: 7.16; 10X WW49: 7.32; 10X WW50: 6.87; 10X WW51: 7.21; 10X WW52: 7.13; 10X WW01: 8.51; 6X WW02: 6.86; 10X WW03: 6.95 | [20 empty] | N/A | N/A |  | 9.69 | 8.15 | 8.31 | 7.45 |  | 7.82 | 7.86 | 8.04 | 7.71 | 7.45 | 7.23 | 7.41 | 7.64 | 7.92
|  | Zone3 | Buffer |  |  |  |  | 6.5 | ww38: N/A; 10X ww39: N/A | [20 empty] | N/A | N/A
MC | [87 empty] | To sequence shuttles to CT1 and CT2 in 2 at a time. | 3sec | 2014-11-18 | Nitipat
[82 empty] | 250.0838 |  |  |  | 243.0451
Meet CT Target
Not meet CT target but with in OTO target
Not meet OTO target
Note on S8: No pivot oreintation
Note on AZ19: Reduce holding time from 2.30 to 2.00 sec.
Note on BO27: Buffer this machine to improve queing issue
Note on BP27: Buffer this machine to improve queing issue
Note on BQ27: Buffer this machine to improve queing issue
Note on BR27: Buffer this machine to improve queing issue
Note on BS27: Buffer this machine to improve queing issue
Note on BT27: Buffer this machine to improve queing issue
Note on BU27: Buffer this machine to improve queing issue
Note on BO28: Buffer this machine to improve queing issue
Note on BP28: Buffer this machine to improve queing issue
Note on BQ28: Buffer this machine to improve queing issue
Note on BR28: Buffer this machine to improve queing issue
Note on BS28: Buffer this machine to improve queing issue
Note on BT28: Buffer this machine to improve queing issue
Note on BU28: Buffer this machine to improve queing issue
Note on Y29: Bond after move fail
Note on AG33: 8.6% retry
Note on AH33: 13.88% Retry
Note on AL33: Retry 25% (72/284)
Note on T35: Switch to use MPT susp on Rembrandt cause difficult to align, need to manual align which cause high CT
Note on AG35: 13.6% retry
Note on AH35: 3.28% Retry
Note on BV35: 6.81% retry
Note on AF37: Pin broken
Note on T38: Trimech team fix on 1st Dec
Note on AF38: Adjust serve position height (pin damage & Flying lead damage)
Note on BJ38: Have board problem which need to be replaced, Currently buffer this zone
Note on BL38: High Q Code Issue
Note on BM38: ACF card problem (waiting spares)
Note on AU39: Vision retry 20%
Note on AT40: downward lookling camera
Note on AU40: Revert back to non-downward camera
Note on BS40: running 6X
Note on BT40: running 6X
Note on BU40: running 6X
Note on BW40: 6X
Note on V41: 17 data point
Note on BS41: running 6X
Note on BT41: running 6X
Note on BU41: running 6X
Note on BW41: 6X
Note on AL46: UV issue 1 chamber, increase MC from 6.5 to 13 sec for compensate
Note on BS49: skip vision process
Note on BT49: skip vision process
Note on BU49: skip vision process
Note on BV49: skip vision process
Note on BW49: skip vision process
Note on BY49: skip vision process
Note on BZ49: skip vision process
Note on CA49: skip vision process
Note on CB49: skip vision process
Note on CD49: skip vision process
Note on CE49: skip vision process
Note on CF49: skip vision process
Note on CG49: skip vision process
Note on CH49: skip vision process
Note on CI49: skip vision process
Note on CJ49: skip vision process
Note on CK49: skip vision process
Note on CL49: skip vision process
Note on AG51: Roll out new eCT software
Note on AH51: Roll out new eCT software
Note on BM52: Sequencing Issue
Note on AF54: Found zero reading and cannot communicate with preamp.
Note on AG54: Found zero reading and communicate with pre-amp
Note on AH54: Roll out new eCT software